## Sheet1
Date | Day | Issue | Solution
2024-02-02 | Day 1 | Problem 1 | I encountered difficulties with the detection of the green square of dimensions 15x15 on a wooden background using Roboflow. In response, I modified the dataset.
2024-02-03 | Day 2 | Problem 2 | Despite changing the background to a wrinkled white cloth, the detection performance for the green square did not improve in Roboflow, prompting further modifications.
2024-02-04 | Day 2 | Problem 3 | While working with a black square of dimensions 15x15 on white paper background, successful detection was achieved also applied preprocessing and data agumentaion techniques such as making rotations to increase the dataset size. However, during the training on Kaggle, some images were not detected due to potential shadow issues. Attempts to rectify this by modifying data in Photoshop resulted in undesirable outcomes. Adjustments were made to iterations and batches, achieving a partial success with two out of three test images being detected.
2024-02-05 | Day 3 | Break
2024-02-06 | Day 4 | Problem 4 | After exploring tutorials on YouTube, I found a helpful video by Nicolai Nielsen, which provided insights into optimizing the use of YOLO. Switching from Kaggle to Google Colab significantly improved detection performance, requiring only 20 iterations compared to Kaggle's 50 for optimal results.
2024-02-06 | Day 4 | Problem 5 | Difficulty arose in identifying the appropriate file to represent the model.
2024-02-06 | Day 4 | Problem 6 | Efforts were made to comprehend how to apply the model in real-time using a camera.
2024-02-06 | Day 4 | Problem 7 | Investigated methods for calculating distance estimation.
2024-02-06 | Day 4 | Problem 8 | Struggled with determining variables such as focal length and size of the square in pixels. Attempted a programmatic approach, which succeeded for pixels but not for focal length. Manual adjustments were made.
2024-02-06 | Day 4 | Problem 9 | Successfully applied the model to a picture but faced challenges with confidence levels, requiring experimentation with different values.
2024-02-06 | Day 4 | Problem 10 | Applied the model to real-time camera footage, initially facing difficulties in closing the camera window.
2024-02-06 | Day 4 | Problem 11 | Resolved issues of program crashes when there were no detections by implementing try and catch in the code.
2024-02-06 | Day 4 | Problem 12 | Focused on integrating label and distance estimation into the real-time window.
2024-02-06 | Day 4 | Problem 13 | Addressed a programming assumption where the code assumed the presence of only one box. Modifications were made to support multiple boxes and estimate distances for each.